## Sheet-1
Project Development and Completion Tracker
Project Start Date: 16/01/2024 Project End Date: 29/04/2024
Porject Descreption: To develop a test portal for online assessments and quizzes in college, using HTML, CSS, JavaScript, React.js, Tailwind CSS, NGINX, Django, Python, Docker, Rest, API.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Samarth nimbargi |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
| Anurag Haldey |  |  |  |  | Frond End
| Ayush Shione |  |  |  |  | Team Lead
| Thomas Cherian |  |  |  |  | Front/Back End
Team Lead
Back End
Front End
Epic: | As a youth and cse student I should know how e-commerce websites functions.
Story 1: | As a youth I understand the need of E-commerce webseties and apps for day to day food ordering.
Story 2: | As a CSE student I should know how this websites functions and works properly.
Story 3: | As a Student, need trusted website to order food items and it should be secure.
Task1: | Design user registration layout with database configuration.
Task2: | Design login page layout.
Task3: | Design region selection layout for address and pincode for dilevery.
Task4: | Design food selection layout which maps with database having different food items and there reviews.
Task5: | Design layout to add the food to cart and calculate total cost.
Task6: | Design layout for checkout page and payment gateway to make the payment which was caluclated in Task5.
Acceptance Criteria:
1 | Registration layout is following all registration inputs with validations for suitable and correct data.
2 | Login layout suports gmail/ contact number/Address of dilevery credential with input validations.
3 | Region selection for address can be easily done by entering pincode .
4 | Food items and restaurant selection layout with rich UX design provide list of products with selection slider.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Design Test Portal layout with database configuration. | Layout Design | Complete | All | 20-02-2024 | 22-02-2024 | 20-02-2024 | 21-02-2024 | 100%
|  | Database configuration | Complete | All | 20-02-2024 | 22-02-2024 | 20-02-2024 | 21-02-2024 | 100%
| Design login page layout. | Layout Design | Complete | All | 01-03-2024 | 04-03-2024 | 01-03-2024 | 03-03-2024 | 100%
|  | Database design and connectivity | Complete | All | 01-03-2024 | 04-03-2024 | 01-03-2024 | 03-03-2024 | 100%
| Design and add functionalities to Home Page along with Database. | Layout Design, Database query | Complete | All | 15-03-2024 | 18--03-2024 | 15-03-2024 | 17-03-2024 | 100%
|  | Database desing and connectivity | Complete | All | 15-03-2024 | 18-03-2024 | 15-03-2024 | 17-03-2024 | 100%
Sprint 1 | Basic Settings(Inside Test) | Layout Design , Database configuration | Complete | All | 2024-04-04 | 07-04-2024 | 2024-04-04 | 06-04-2024 | 100%
| Questions Manager(Inside Test) | Load Balancing(Session Persistance)along with Database configuration | Complete | All | 04-04-2024 | 07-04-2024 | 04-04-2024 | 06-04-2024 | 100%
| Time settings(Inside Test) | Layout Design and functionality | Complete | All | 23-04-2024 | 27-04-2024 | 23-04-2024 | 26-04-2024 | 100%
Sprint 2 | Results and User Database | Database configuration | Complete | All | 23-04-2024 | 27-04-2024 | 23-04-2024 | 26-04-2024 | 100%